## Project Checklist
Done | Phase | Milestone / Week | Task | Day / Timeframe | Track | Priority | Notes
| PRE-LAUNCH | WEEK 1: FOUNDATION
✓ | Pre-Launch | Week 1 | Generate 4 core brand images (logo, Cosmo, banner, marriage concept) in Nano Banana 2 | Day 1 | Infrastructure | P0 | Apr 10, 2026
✓ | Pre-Launch | Week 1 | Generate 3 character portraits (Nova, Stella, Luna) | Day 1 | Infrastructure | P0 | Apr 10, 2026
✓ | Pre-Launch | Week 1 | Set up OpenSea collection (Turbomindz Odyssey, Polygon, 5% royalties) | Day 1 | Infrastructure | P0 | Apr 10, 2026
✓ | Pre-Launch | Week 1 | Create Twitter/X @turbomindz account with brand assets | Day 1 | Infrastructure | P0 | Apr 10, 2026
| Pre-Launch | Week 1 | Update Instagram @turbomindz (business account, new bio, teaser post) | Day 2 | Infrastructure | P0
| Pre-Launch | Week 1 | Create Pinterest business account + 10 SEO boards + 12 vertical pins | Day 2 | Infrastructure | P0
| Pre-Launch | Week 1 | Create Linktree with all platform links + brand colors | Day 2 | Infrastructure | P0
| Pre-Launch | Week 1 | Set up Buttondown newsletter + write welcome email | Day 2 | Infrastructure | P0
| Pre-Launch | Week 1 | Build pre-launch hype site on Carrd.co with full copy | Day 3 | Infrastructure | P0
| Pre-Launch | Week 1 | Create Discord server (8 categories, 38+ channels) | Day 4 | Infrastructure | P0
| Pre-Launch | Week 1 | Configure Discord roles and permissions (8 roles) | Day 4 | Infrastructure | P0
| Pre-Launch | Week 1 | Write Discord welcome message + rules + charter | Day 4 | Infrastructure | P0
| Pre-Launch | Week 1 | Set up Guild.xyz token gating for @Collector role | Day 5 | Infrastructure | P0
| Pre-Launch | Week 1 | Test Guild.xyz wallet verification flow end-to-end | Day 5 | Infrastructure | P0
| Pre-Launch | Week 1 | Set up Patreon (5 tiers: $3/$7/$15/$30/$50) | Day 5 | Infrastructure | P0
| Pre-Launch | Week 1 | Set up Ko-fi (tip jar + shop) | Day 5 | Infrastructure | P1
| Pre-Launch | Week 1 | Create Gumroad account + profile | Day 6 | Infrastructure | P1
| Pre-Launch | Week 1 | Create first free lead magnet PDF (Phygital Art 101) | Day 6 | Content | P1
| Pre-Launch | Week 1 | Create second lead magnet PDF (9 Questions That Changed Everything) | Day 6 | Content | P1
| Pre-Launch | Week 1 | Create Medium account + first article | Day 7 | Infrastructure | P1
| Pre-Launch | Week 1 | Set up Buffer (3 channels) + schedule first week | Day 7 | Infrastructure | P1
| Pre-Launch | Week 1 | Add Discord invite link to ALL platforms | Day 7 | Infrastructure | P0
| PRE-LAUNCH | MILESTONE: All 12+ platforms live and linked |  | Day 7
| PRE-LAUNCH | WEEK 2: FIRST NFTs + CONTENT ENGINE
| Pre-Launch | Week 2 | Generate Episode 1 / Shots 1-4 images (TM-001 to TM-004) in Nano Banana 2 | Day 8 | Production | P0
| Pre-Launch | Week 2 | Generate video clips for TM-001 to TM-004 in Higgsfield.ai | Day 8 | Production | P0
| Pre-Launch | Week 2 | List TM-001 to TM-004 on OpenSea (full metadata + traits) | Day 8 | Production | P0
| Pre-Launch | Week 2 | Post first scene reveal on Instagram + Twitter + Discord | Day 8 | Content | P0
| Pre-Launch | Week 2 | Produce TM-005 to TM-008 (THE WONDER segment) | Day 9 | Production | P0
| Pre-Launch | Week 2 | Produce TM-009 to TM-012 (THE QUESTION + DEEPENING) | Day 10 | Production | P0
| Pre-Launch | Week 2 | Produce TM-013 to TM-016 (DEEPENING + FADE) — Stella arrives TM-016 | Day 11 | Production | P0
| Pre-Launch | Week 2 | Produce TM-017 to TM-020 (STRUGGLE segment) | Day 12 | Production | P0
| Pre-Launch | Week 2 | Produce TM-021 to TM-024 (THE FORGE segment) | Day 13 | Production | P0
| Pre-Launch | Week 2 | Produce TM-025 to TM-028 (THE WITNESS segment) | Day 14 | Production | P0
| Pre-Launch | Week 2 | Assemble Episode 1 video in DaVinci Resolve (28 clips) | Day 14 | Production | P0
| Pre-Launch | Week 2 | Upload Episode 1 to YouTube (title, description, thumbnail) | Day 14 | Content | P0
| Pre-Launch | Week 2 | Send first Odyssey Dispatch newsletter via Buttondown | Day 14 | Content | P0
| PRE-LAUNCH | MILESTONE: Episode 1 complete (28 NFTs listed, video on YouTube) |  | Day 14
| PRE-LAUNCH | WEEKS 3-4: EPISODE 2 + PWA DEVELOPMENT
| Pre-Launch | Week 3-4 | Produce Episode 2 NFTs: TM-029 to TM-056 (4/day, Days 15-21) | Days 15-21 | Production | P0
| Pre-Launch | Week 3-4 | Set up Next.js 14 project + Tailwind with Turbomindz theme | Day 15 | Development | P0
| Pre-Launch | Week 3-4 | Build root layout (dark mode, fonts) + Header + Footer | Day 16 | Development | P0
| Pre-Launch | Week 3-4 | Build Homepage (hero, membership explainer, 9 questions, characters, newsletter) | Days 17-18 | Development | P0
| Pre-Launch | Week 3-4 | Build Gallery page (grid layout, NFT card, FilterBar component) | Days 19-20 | Development | P0
| Pre-Launch | Week 3-4 | Assemble Episode 2 video + upload to YouTube | Day 21 | Production | P0
| Pre-Launch | Week 3-4 | Build Scene Detail page (full NFT metadata display) | Day 22 | Development | P0
| Pre-Launch | Week 3-4 | Build About page (mission, three pillars, FAQ) | Day 23 | Development | P1
| Pre-Launch | Week 3-4 | Build Episodes page (39 cards, season tabs) | Day 24 | Development | P1
| Pre-Launch | Week 3-4 | Build Marriage page (self-service explainer) | Day 25 | Development | P1
| Pre-Launch | Week 3-4 | Configure Serwist PWA service worker + manifest.ts | Day 26 | Development | P0
| Pre-Launch | Week 3-4 | SEO: meta tags + Open Graph images + Pinterest domain verification tag in layout.tsx | Day 27 | Development | P1
| Pre-Launch | Week 3-4 | Run npm run build — fix all errors. Static site complete. | Day 28 | Development | P0
| PRE-LAUNCH | MILESTONE: Episode 2 complete + PWA Phase 1 (static site) built |  | Day 28
| PRE-LAUNCH | WEEK 5: WEB3 INTEGRATION
| Pre-Launch | Week 5 | Create Supabase project + 6 database tables + Row Level Security | Day 29 | Development | P0
| Pre-Launch | Week 5 | Create Pinata + thirdweb accounts, get OpenSea API key, configure .env.local | Day 30 | Development | P0
| Pre-Launch | Week 5 | Build thirdweb wallet connection (WalletConnectButton) | Day 31 | Development | P0
| Pre-Launch | Week 5 | Build OpenSea API proxy route + live gallery data | Day 32 | Development | P0
| Pre-Launch | Week 5 | Build PurchaseModal (Seaport + OpenSea redirect) | Day 33 | Development | P0
| Pre-Launch | Week 5 | Build membership verification (useOwnedNFTs + MembershipGate) | Day 34 | Development | P0
| Pre-Launch | Week 5 | Build account creation flow + npm run build — zero errors | Day 35 | Development | P0
| PRE-LAUNCH | MILESTONE: PWA Phase 2 complete (Web3 integration live) |  | Day 35
| PRE-LAUNCH | WEEK 6: BUFFER CONTENT + HYPE CAMPAIGN
| Pre-Launch | Week 6 | Resume NFT production: TM-057 to TM-080 (4/day, Days 36-41) | Days 36-41 | Production | P0
| Pre-Launch | Week 6 | Write Launch Announcement blog post for Medium | Day 36 | Content | P1
| Pre-Launch | Week 6 | Create 5 social teaser images for countdown | Day 37 | Content | P0
| Pre-Launch | Week 6 | Schedule countdown posts on Buffer (7 days, 6 days...) | Day 38 | Content | P0
| Pre-Launch | Week 6 | Post Episode 1 trailer (60s) on Twitter, Instagram Reels, TikTok | Day 39 | Content | P0
| Pre-Launch | Week 6 | DM 10 NFT/art accounts on Twitter inviting to launch | Day 40 | Content | P1
| Pre-Launch | Week 6 | Post Behind the Scenes thread on Twitter | Day 41 | Content | P1
| Pre-Launch | Week 6 | Update Carrd site with real NFT images + YouTube trailer embed | Day 42 | Infrastructure | P0
| PRE-LAUNCH | WEEK 7: FINAL PRE-LAUNCH
| Pre-Launch | Week 7 | Deploy PWA to Vercel + connect domain (or .vercel.app) | Day 43 | Development | P0
| Pre-Launch | Week 7 | Test: site loads, gallery shows real NFTs, wallet connects, purchase works | Day 43 | Development | P0
| Pre-Launch | Week 7 | Verify Pinterest domain claim (Settings → Claimed Accounts → turbomindz.com) | Day 43 | Infrastructure | P0
| Pre-Launch | Week 7 | Replace Carrd with real site, update all platform links | Day 43 | Infrastructure | P0
| Pre-Launch | Week 7 | Final QA: test on mobile (iOS + Android), test PWA install, fix bugs | Day 44 | Development | P0
| Pre-Launch | Week 7 | LAUNCH EVE: final countdown on all platforms + newsletter to waitlist | Day 45 | Content | P0
| Pre-Launch | Week 7 | Prepare Day 46 social posts in Buffer | Day 45 | Content | P0
| PRE-LAUNCH | MILESTONE: ALL PRE-LAUNCH COMPLETE — Ready for Launch Day |  | Day 45
| LAUNCH DAY | LAUNCH DAY
| Launch Day | Day 46 | Post LIVE NOW on ALL platforms (Instagram, Twitter, Discord, Pinterest, Medium) | Day 46 | Content | P0
| Launch Day | Day 46 | Share YouTube Episode 1 link + OpenSea collection link + website link | Day 46 | Content | P0
| Launch Day | Day 46 | Engage with all comments, DMs, mentions — thank every early supporter | Day 46 | Content | P0
| Launch Day | Day 46 | Post Day 1 sales update on Discord | Day 46 | Content | P0
| LAUNCH DAY | MILESTONE: TURBOMINDZ IS LIVE (56 NFTs, 2 episodes, PWA, Discord) |  | Day 46
| GROWTH | GROWTH PHASE: DAILY PRODUCTION
| Growth | Daily Routine | Establish daily 2h routine: Claude tasks -> 4 images -> list on OpenSea -> 4 videos -> social -> engage | Day 47+ | Production | P0
| Growth | Episodes | Assemble Episode 3 (U3: Floating Sumi-e Cosmos) | ~Day 53 | Production | P0
| Growth | Episodes | Assemble Episode 4 (U4: Stardust Impressionism) | ~Day 60 | Production | P0
| Growth | Episodes | Assemble Episode 5 (U5: Botanical Bioluminescence) | ~Day 67 | Production | P0
| Growth | Episodes | Assemble Episode 6 (U6: Geometric Sacred) | ~Day 74 | Production | P0
| Growth | Episodes | Assemble Episode 7 (U7: Crystalline Dreamscape) | ~Day 81 | Production | P0
| Growth | Episodes | Assemble Episode 8 (U8: Mechanical Botanical) | ~Day 88 | Production | P0
| Growth | Pinterest | Establish daily Pinterest routine: 1 pin/day (2:3 vertical) + 2-3 curated repins | Day 47+ | Content | P0
| Growth | Pinterest | Create first weekly Idea Pin (multi-slide format, 9x engagement) | Week 8 | Content | P0
| Growth | Pinterest | Reach 30+ pins per board across all 10 boards (original + curated mix) | Month 2-3 | Content | P1
| Growth | Pinterest | First Pinterest analytics review — top pins, keywords, board traffic | Month 2 end | Content | P1
| Growth | Pinterest | Optimize pin descriptions and board keywords based on analytics | Month 3 | Content | P1
| Growth | Pinterest | Reach 5,000+ monthly impressions on Pinterest | Month 3 | Content | P1
| GROWTH | PWA PHASE 3-4 DEVELOPMENT
| Growth | PWA Dev | Build marriage self-service form (photo upload, auto-confirm, on-chain) | Days 47-55 | Development | P0
| Growth | PWA Dev | Build CardFlip component for married NFTs | Days 56-62 | Development | P1
| Growth | PWA Dev | Build member profiles + owned NFTs display | Days 63-70 | Development | P1
| Growth | PWA Dev | Build marketplace for married NFTs (listing + bid system) | Days 71-78 | Development | P0
| Growth | PWA Dev | Build community forum (Discord sync via webhook) | Days 79-85 | Development | P2
| Growth | PWA Dev | Performance optimization + Lighthouse audit + PWA polish | Days 86-90 | Development | P1
| GROWTH | MILESTONE: 232 NFTs live, 8 episodes complete, PWA fully functional |  | Day 90
| CRUISE | CRUISE PHASE: STEADY PRODUCTION
| Cruise | Season 1 | Complete Season 1 (Episodes 9-13, ~TM-232 to TM-370) | Days 91-137 | Production | P0
| CRUISE | MILESTONE: SEASON 1 FINALE — 370 NFTs, 13 episodes |  | Day 137
| Cruise | Season 2 | Complete Season 2 (Episodes 14-26, ~TM-371 to TM-740) | Days 138-230 | Production | P0
| Cruise | Season 2 | Episode 26: THE TWIST — The Fade is transformation, not destruction | ~Day 230 | Production | P0
| CRUISE | MILESTONE: SEASON 2 FINALE + THE TWIST — 740 NFTs, 26 episodes |  | Day 230
| Cruise | Season 3 | Complete Season 3 (Episodes 27-39, ~TM-741 to TM-1111) | Days 231-323 | Production | P0
| Cruise | Season 3 | 1,000th NFT listed | ~Day 315 | Production | P0
| Cruise | Season 3 | Episode 39: FINALE — Cosmo removes helmet. Luna closes notebook. | ~Day 323 | Production | P0
| CRUISE | MILESTONE: ALL 1,111 NFTs LISTED — 39 episodes complete |  | Day 323
| Cruise | Pinterest | Reach 100+ outbound clicks/month from Pinterest to sales platforms | Month 4-5 | Content | P1
| Cruise | Pinterest | Reach 15,000+ monthly impressions on Pinterest | Month 6 | Content | P2
| Cruise | Pinterest | Create Pinterest-exclusive Idea Pin series (monthly) | Month 4+ | Content | P2
| Cruise | Pinterest | Quarterly Pinterest board audit: prune underperforming boards, add trending topics | Month 6, 9, 12 | Content | P2
| MONETIZATION | REVENUE MILESTONES
| Monetization | Revenue | Upload 15 digital products to Gumroad | Week 2-3 | Content | P0
| Monetization | Revenue | Upload 10 POD products to Etsy via Printful | Week 2-3 | Content | P1
| Monetization | Revenue | Publish first 3 guides on Amazon KDP | Week 3-4 | Content | P1
| Monetization | Revenue | Launch first Easter Egg Hunt contest | ~Day 53 | Content | P1
| Monetization | Revenue | Launch first Philosophy Challenge (7-day) | ~Day 60 | Content | P1
| Monetization | Revenue | Host First Marriage event + livestream | ~Day 65 | Content | P0
| Monetization | Revenue | Begin artist partnership outreach (10 artists) | ~Day 70 | Content | P1
| Monetization | Revenue | ProductHunt launch | ~Day 90 | Content | P1
| Monetization | Revenue | Monthly transparency report (Month 1) | Month 1 end | Content | P0
| Monetization | Revenue | Monthly transparency report (Month 2) | Month 2 end | Content | P0
| Monetization | Revenue | Monthly transparency report (Month 3) | Month 3 end | Content | P0
| MONETIZATION | MILESTONE: Break-even (~$1,000/month revenue) |  | Month 3-4
| MONETIZATION | MILESTONE: First $10K cumulative revenue |  | Month 6
| MONETIZATION | MILESTONE: Part-time income ($5,000+/month) |  | Month 9-10
| MONETIZATION | MILESTONE: Full-time viable ($7,700+/month) |  | Month 12
| COMMUNITY | COMMUNITY GOVERNANCE
| Community | Governance | Appoint first 3 Moderators | Week 4-6 | Infrastructure | P0
| Community | Governance | Nominate + vote on first 5 Elders | Month 2-3 | Infrastructure | P1
| Community | Governance | Nominate + vote on first 5 Scribes | Month 2-3 | Infrastructure | P1
| Community | Governance | First community Snapshot vote | Month 3 | Infrastructure | P1
| Community | Governance | Publish first quarterly governance transparency report | Month 3 | Content | P1
| Community | Governance | Marriage system fully community-governed (no founder involvement) | Month 4-5 | Infrastructure | P0

## Dashboard
TURBOMINDZ PROJECT DASHBOARD
Total Tasks | 120 | Tasks by Phase
|  | Pre-Launch | 70
Total Milestones | 14 | Launch Day | 4
|  | Growth | 19
Production Days | ~323 | Cruise | 10
|  | Monetization | 11
NFTs to Produce | 1,111 | Community | 6
Tasks by Track
|  | Infrastructure | 28
HOW TO USE |  | Content | 39
1. Type an "X" or any character in the "Done" column (A) to mark a task complete. |  | Production | 26
2. Use the Notes column (H) to capture blockers, links, or status updates. |  | Development | 27
3. Filter by Phase, Track, or Priority using the dropdown arrows in the header row.
4. P0 = Must do (critical path), P1 = Should do, P2 = Nice to have.
5. Milestone rows (pink) mark key checkpoints — celebrate when you reach them!

## Timeline
KEY MILESTONES TIMELINE
Day | Milestone | NFTs Live | Episodes | Revenue Target
7 | All platforms live | - | - | -
14 | Episode 1 complete | 28 | 1 | -
28 | Episode 2 + PWA Phase 1 | 56 | 2 | -
35 | Web3 integration live | 56 | 2 | -
45 | Pre-launch complete | 80+ | 2+ | -
46 | LAUNCH DAY | 56+ | 2 | $200
60 | Month 2 | ~112 | 4 | $765 cumul.
90 | Growth phase complete | ~232 | 8 | $1,820 cumul.
137 | SEASON 1 FINALE | ~370 | 13 | $6,555 cumul.
230 | SEASON 2 FINALE (THE TWIST) | ~740 | 26 | $24,173 cumul.
315 | 1,000th NFT | ~1,000 | 36 | $36,958 cumul.
323 | ALL 1,111 NFTs COMPLETE | 1,111 | 39 | $44,703 cumul.